## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 2024-12-08 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | One or more team members added to the team | 2 | 3 | 2 | 2*3*2=12 | team leader and all members |  | Redefine the project scope by assessing progress, prioritizing essential tasks, and reallocating work based on new team members' skills. | A new team member has been added, with tasks reassigned from previous team members to ensure clear ownership and seamless execution, supported by ongoing communication and collaboration. | Open
| Lack of motivation or responsibility | Some team members lose motivation or do not take responsibility for tasks | 3 | 4 | 3 | 36 |  |  |  | No issues so far; initial team motivation and responsibilities are clear. | Open
Communication | duplicate work | Team members work on the same components, leading to waste of time | 2 | 4 | 3 | 24 |  |  | Use task management tools (e.g., Trello, Jira) and maintain communication on task assignments. | Clear task allocation; no duplicate work reported yet. | Open
| worked on wrong components | Team members work on components that do not align with the project’s goals | 2 | 5 | 2 | 20 |  |  | Hold frequent sync-ups to clarify tasks and verify if everyone is working on the correct components. | Sync-ups scheduled weekly to ensure no misalignment. | Open
Requirements | unclear requirements | Requirements are not well-defined or constantly changing | 3 | 5 | 3 | 45 |  |  | Confirm requirements with the course instructor before starting major tasks; freeze core features early. | Initial project scope has been defined; requirements subject to clarification during feedback. | Open
Requirements | constant requirements changes | Requirements are changed due to some unforeseen circumstances | 2 | 3 | 2 | 24
Management | improper task assignments | Tasks are not assigned to the team members best suited for them | 2 | 4 | 2 | 16 |  |  | Ensure each team member’s strengths are considered when assigning tasks. Reassess roles if necessary. | Initial task assignments aligned with team member skill sets. | Open
improper planning
lack of management skills
Technology competence | Not familiar with the framework used | Team members lack experience with key frameworks or technologies being used | 3 | 4 | 3 | 36 |  |  | Allocate time for learning or prototyping with new frameworks before main development starts. | Team members assigned learning tasks for unfamiliar frameworks. | Open
Not familiar with the programming language used
Not familiar with unit testing
Other technology incompetence
Not familiar with Git
Design and implementation | Improper design
improper technology stack
| Messy code | This will delay the process of repairing bugs in the future. When writing code, it's important to follow proper formatting and adhere to practices to maintain readability and efficiency. | 3 | 5 | 1 | 15 | Pratyush |  | Set coding standards and enforce code reviews before merging any new code. | No coding issues so far; project setup phase completed. | Open
Testing | Not enough testing
Integration and deployment | Not enough time for integration and deployment | The team does not allocate enough time for testing and deployment at the end of the project | 2 | 5 | 3 | 30 |  |  | Reserve the last 1-2 weeks solely for integration and deployment, even if features are incomplete. | Timeline for deployment set, with 1 week buffer for unforeseen delays. | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.